## Slide 1: Project Status Report
UWA | Exchange Unit Approval Process
17th September 2018

## Slide 2: Project Status Report UWA | Exchange Unit Approval Process
 | Weeks |  |  |  |  |  |  |  |  |  |  |  | 
Activities Weeks | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | Break | 9 | 10 | 11 | 12
Unit Search Interface |  |  |  |  |  |  |  |  |  |  |  |  | 
Unit Application Form |  |  |  |  |  |  |  |  |  |  |  |  | 
Staff Portal |  |  |  |  |  |  |  |  |  |  |  |  | 
Unit Approvals Database |  |  |  |  |  |  |  |  |  |  |  |  | 
Testing |  |  |  |  |  |  |  |  |  |  |  |  | 
User Acceptance Testing, Training and Documentation |  |  |  |  |  |  |  |  |  |  |  |  | 
Current
Sprint 1
End
Sprint 2
End
Sprint 3
End
Unit Search Interface /
Unit Application Form
Staff Portal
Unit Equivalence Decision Form
Unit Approvals Database
Training, Testing and Documentation
Legend:
Not Started
Delayed
Completed
In Progress
Fully implemented Student is unable to submit application as of yet | Development started Scope expanded, more requirements to be met | Abandoned in favour of additional staff portal scope Being replaced by clipboard functionality to paste into emails | Database received from Arts Faculty Implemented into system Queries to read DB complete | Basic automated testing in development
Abandoned

## Slide 3: Project Status Report UWA | Exchange Unit Approval Process
Components Overview
Student Application Form
Staff Portal
Unit Equivalence Decision Form
Unit Approvals Database
Unit Search Interface
Legend:
Not Started
Delayed
Completed
In Progress
Abandoned
Approvals Inbox
Application Overview
Clipboard to Email